## CYCLETIME
|  |  | Working hr per WK | 57 | 57 | 57 | 66 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 57
|  |  | work day per wk | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5
|  |  | working hr per day | 9.5 | 9.5 | 9.5 | 11 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5
PART NUMBER | BATCH | QTY |  | LASER START | LASER END | TAPPING | CNC 1 END | SAND BLASTING END | ROBOT WELDING 1 END | MANUAL WELDING END | MANUAL WELDING 2 | GRINDING END | CNC 2 END | BUFFING END | QA END | PLATING END | ASSEMBLY | OUTGOING QA END | PACKING END | SHIPMENT | REMARK
FMWB3830103000-04-0G | FLEX UPPER LOT 1 | 1 | CYCLE TIME (HOURS) | 9.5 | 9.5 | NA | 9.5 | 9.5 | 9.5 | 9.5 | NA | 4.5 | 13 | 9.5 | 4 | 6 | NA | 4
FMWB3840100000-05-0K | FLEX LOWER LOT 1 | 1 | CYCLE TIME (HOURS) | 9.5 | 9.5 | NA | 9.5 | 9.5 | 9.5 | 13.5 | NA | 4.5 | 4.5 | 9.5 | 4 | 6 | NA | 4
FM079790401010-01-0C | POWER M | 1 | CYCLE TIME (HOURS) | 9.5 | 9.5 | 9.5 | NA | 9.5 | 19 | 9.5 | 19 | NA | 4 | 9.5 | NA | 5 | 5 | NA | NA
you may understand from this worksheet, each process cycle time for each model (per set)
example:
FMWB3830103000-04-0G, CAM need 9 hours, laser need 9.5 hours
laser working hours per day is 9.5 hours
you may also refer to "production order",
Example:
RPO-2026-011764, total quantity needed is 5 sets, which planned start at 24/08/2026. So for LASER, you need multiple LASER hours * quantity 9.5 * 5 = 47.5 hours, means planned laser will complete at 24/08/2026
Please exclude if the date fall at "public holiday" list
we need to show all planning in calender made as "scheduelling system" worksheet

## PRODUCTION ORDER
Prod. Order No. | Item No. | Description 2 | Starting Date-Time | Quantity
RPO-2026-011764 | FMWB3830103000-04-0G | Y390 UPPER LOT22 | 2026-08-24 18:00 | 1
RPO-2026-013305 | FMWB3830103000-04-0G | Y390 UPPER LOT23 | 2026-08-27 18:00 | 1
RPO-2026-013306 | FMWB3830103000-04-0G | Y390 UPPER LOT24 | 2026-09-08 18:00 | 1
RPO-2026-013307 | FMWB3830103000-04-0G | Y390 UPPER LOT25 | 2026-09-18 18:00 | 1
RPO-2026-013308 | FMWB3830103000-04-0G | Y390 UPPER LOT26 | 2026-09-23 18:00 | 1
RPO-2026-013309 | FMWB3830103000-04-0G | Y390 UPPER LOT27 | 2026-09-29 18:00 | 1
RPO-2026-011760 | FMWB3840100000-05-0K |  | 2026-08-24 18:00 | 1
RPO-2026-013310 | FMWB3840100000-05-0K | Y390 LOWER LOT23 | 2026-08-27 18:00 | 1
RPO-2026-013311 | FMWB3840100000-05-0K | Y390 LOWER LOT24 | 2026-09-08 18:00 | 1
RPO-2026-013312 | FMWB3840100000-05-0K | Y390 LOWER LOT25 | 2026-09-18 18:00 | 1
RPO-2026-013313 | FMWB3840100000-05-0K | Y390 LOWER LOT26 | 2026-09-23 18:00 | 1
RPO-2026-013314 | FMWB3840100000-05-0K | Y390 LOWER LOT27 | 2026-09-29 18:00 | 1
RPO-2026-010771 | FM079790401010-01-0C | POWER M LOT 12 | 2026-08-17 18:00 | 1
RPO-2026-010772 | FM079790401010-01-0C | POWER M LOT 13 | 2026-08-17 18:00 | 1

## PUBLIC HOLIDAY
Date | Weekdays | Remark
2026-02-17 | 2 | PH
2026-02-18 | 3 | PH
2026-03-21 | 6 | PH
2026-03-22 | 7 | PH
2026-03-23 | 1 | PH
2026-03-24 | 2 | PH
2026-05-01 | 5 | PH
2026-05-27 | 3 | PH
2026-05-31 | 7 | PH
2026-06-01 | 1 | Replacement
2026-06-02 | 2 | Replacement
2026-06-17 | 3 | PH
2026-08-25 | 2 | PH
2026-08-31 | 1 | PH
2026-09-16 | 3 | PH
2026-11-08 | 7 | PH
2026-11-09 | 1 | Replacement
2026-12-25 | 5 | PH